## MileStoneAndWorkAssignment
Workload and Milestone Sheet
Event Name | Start Date | End Date | Requirement ID | Assign To | State
Sprint One | Oct.28 2013 | Nov.3 2013 | F00001 Client&Server | Jianghua Kua | Finished
|  |  | F00002 Server | Jianghua Kuai | Finished
|  |  | F00002 Client | Shuai Zhao | Finished
Sprint Two | Nov.4 2013 | Nov.10 2013 | F00004 Server | Jianghua Kuai | Finished
|  |  | F00003 Client&Server | Jianghua Kuai | Finished
|  |  | F00004 Client | Shuai Zhao | Finished
Sprint Three | No.11 2013 | Nov.17 2013 | F00005 Client&Server | Jianghua Kuai | Finished
|  |  | F00007 Server | Jianghua Kuai | Finished
|  |  | F00007 Client | Shuai Zhao | Finished
Sprint Four | Nov.18 2013 | Nov.24 2013 | F00006 Client&Server | Jianghua Kuai | Finished
|  |  | Test case Document | Shuai Zhao | Finished
|  |  | Manual Document | Shuai Zhao | Finished
Final Sprint | Nov.25 2013 | Nov.30 2013 | Make up all document | Jianghua Kuai&Shuai Zhao | Finished