## MileStoneAndWorkAssignment
Event Name | Start Date | End Date | Requirement ID | Assign To | State | We'll use agile development method, so we'll release useable product every week. Every teammate will contribute to the product, so we assign the job by the requirements(also known as user story). Teammate should use unit test to test their code first.
Sprint One | Oct.28 2013 | Nov.3 2013 | F00001 | Jianghua Kuai | Processing
|  |  | F00002 | Shuai Zhao | Processing
Sprint Two | Nov.4 2013 | Nov.10 2013 | F00003 | Jianghua Kuai | Processing
|  |  | F00004 | Shuai Zhao | Processing
Sprint Three | No.11 2013 | Nov.17 2013 | F00005 | Jianghua Kuai | Processing
|  |  | F00007 | Shuai Zhao | Processing
Sprint Four | Nov.18 2013 | Nov.24 2013 | F00006 | Jianghua Kuai | UnFinished
|  |  | Manual Document | Shuai Zhao | UnFinished
Final Sprint | Nov.25 2013 | Nov.30 2013 | Make up all document | Jianghua Kuai&Shuai Zhao | UnFinished